## Sheet1
Phase | Task | Status | Findings (What I observed) | Improvement / Fix
Analyze (DL1) | Define problem scope and goal | Done | Academic benchmarks do not reflect real coding usefulness | Focus project on real-world coding evaluation
Analyze (DL1) | Identify evaluation gap | Done | Existing benchmarks measure correctness, not usefulness | Shift toward practical evaluation approach
Advise (DL2) | Compare evaluation methods | Done | BLEU / HumanEval do not capture practical usefulness | Select LLM-as-judge as better fit
Advise (DL2) | Test evaluation approach (small sample) | Done | Judge scoring works but may be strict or inconsistent in some cases | Have more clear rubric prompt and check the fully pipeline to see if it have bias
Design (DL3) | Define dataset and categories | Done | Questions vary in difficulty and type | Structure into debugging, conceptual, implementation
Design (DL3) | Test models on small sample (3 questions) | Done | Judge tends to score explanation quality strictly | Adjust expectations and keep rubric consistent
Design (DL3) | Define evaluation pipeline | Done | Pipeline logic works conceptually but not tested yet | Move to full implementation
Realize (DL4) | Run full pipeline on dataset | Done | Generated full outputs but difficult to interpret results quickly | Add summary output for easier reading
Realize (DL4) | Implement LLM judge scoring | Done | Scores generated consistently but require inspection | Build tools for result visibility
Realize (DL4) | Add print_summary() function | Done | Summary was not visible in raw CSV | Display acceptance rate and average score in terminal
Realize (DL4) | Build dashboard (Streamlit) | Done | Easier to inspect results, but revealed hidden issues | Use dashboard as main inspection tool
Debug & Improve(DL4) | Inspect outputs in dashboard | Done | Found Q21 bug (empty response shown as 'nan') | Investigate API and evaluation logic
Debug & Improve(DL4) | Identify judge reliability issue | Done | Judge scored empty answer as 3 (invalid) | Add skip logic for empty responses
Debug & Improve(DL4) | Fix pipeline errors | Done | Empty responses were incorrectly processed | Add guard in answer.py and skip in evaluate.py
Validate(D4) | Review model performance differences | Done | Large gap between models and task specialization observed | Use findings as benchmark insight
Manage & Validate(DL5) | Assess system reliability | Done | Audited eval.csv vs prompt.csv with check_evidence.py - found 29/90 rows mismatched (Q21-Q30, all 3 models); prompt.csv is from a later run that hit Connection errors, eval.csv is the complete consistent run (90/90 scored, 0 skips) | Adopted eval.csv as canonical evidence source; documented finding + recommended adding a run-ID to every pipeline output row so paired files can be verified automatically in future runs (see Decision Log 5)